## Master Timeline
Master Timeline and Submission Deadlines
Programme start: Monday 13 July 2026. All deadlines 17:00 Indochina Time (ICT) unless noted.
ID | Week | Date | Day | Time | Task | Workflow | Owner | Deliverable | Submit to | Format | Buddy check-in
W1-01 | Week 1 | 13 Jul 2026 | Monday | 17:00 | Programme kickoff and data room access | All | Engagement Lead | - | Session | -
W1-02 | Week 1 | 13 Jul 2026 | Monday | EOD | Read handbook, index and workflow briefs | All | All | - | Team drive | Internal
W1-03 | Week 1 | 14 Jul 2026 | Tuesday | 17:00 | Submit signed Project Charter | All | PM Lead | Project_Charter | Buddy + drive | PDF
W1-04 | Week 1 | 14 Jul 2026 | Tuesday | 17:00 | Submit populated RACI matrix | All | Engagement Lead | RACI_Matrix | Buddy + drive | Excel
W1-05 | Week 1 | 15 Jul 2026 | Wednesday | 17:00 | Submit problem statement and issue tree | A | WF-A Lead | A1 Issue tree | Buddy + drive | PDF
W1-06 | Week 1 | 16 Jul 2026 | Thursday | 17:00 | Submit information credibility matrix | All | Research Lead | Credibility matrix | Buddy + drive | PDF
W1-07 | Week 1 | 17 Jul 2026 | Friday | 12:00 | Confirm A/B protocol and Request Log owners | All | Engagement Lead | - | Buddy | - | Check-in 1
W1-08 | Week 1 | 17 Jul 2026 | Friday | 17:00 | Update Master Timeline with named owners | All | PM Lead | This workbook | Buddy + drive | Excel
W2-01 | Week 2 | 20 Jul 2026 | Monday | 17:00 | File Analysis Request R-01 | A | WF-A Lead | Analysis_Request | Team drive | PDF
W2-02 | Week 2 | 20 Jul 2026 | Monday | - | Profile all eight dataset tables (DB-1) | B | WF-B Lead | Profiling notes | Team drive | Excel
W2-03 | Week 2 | 21 Jul 2026 | Tuesday | 17:00 | Submit data quality report (B internal) | B | WF-B Lead | B1 Data quality | Buddy + drive | PDF
W2-04 | Week 2 | 22 Jul 2026 | Wednesday | 17:00 | Submit interview synthesis | A | Research Lead | A2 Synthesis | Buddy + drive | PDF
W2-05 | Week 2 | 22 Jul 2026 | Wednesday | 17:00 | Submit empathy and journey maps | A | WF-A Lead | A3 Maps | Buddy + drive | PDF
W2-06 | Week 2 | 23 Jul 2026 | Thursday | 17:00 | Return Findings Memo FM-01 | B | WF-B Lead | Findings_Memo | Team drive | PDF
W2-07 | Week 2 | 24 Jul 2026 | Friday | 17:00 | Submit dashboard version 1 (B working file) | B | WF-B Lead | B2 Dashboard | Buddy + drive | Excel | Check-in 2
W3-01 | Week 3 | 27 Jul 2026 | Monday | 17:00 | File Analysis Requests R-02 and R-03 | A | WF-A Lead | Analysis_Request | Team drive | PDF
W3-02 | Week 3 | 28 Jul 2026 | Tuesday | 17:00 | Return FM-02 and FM-03; analysis summary | B | WF-B Lead | B3 + Findings | Buddy + drive | Excel+PDF
W3-03 | Week 3 | 30 Jul 2026 | Thursday | 17:00 | Submit strategic options (cite Request IDs) | A | WF-A Lead | A4 Options | Buddy + drive | PDF
W3-04 | Week 3 | 31 Jul 2026 | Friday | 17:00 | Submit evidence-check memo on options | B | WF-B Lead | B4 Evidence check | Team drive | PDF | Check-in 3
W4-01 | Week 4 | 05 Aug 2026 | Wednesday | 17:00 | Submit validation protocol and trade-off reflection | A | Research / WF-A | A5 A6 | Buddy + drive | PDF
W4-02 | Week 4 | 06 Aug 2026 | Thursday | 17:00 | Submit funding scenarios (DB-5) | B | Ops Analyst | B5 Funding | Buddy + drive | Excel
W4-03 | Week 4 | 06 Aug 2026 | Thursday | 17:00 | Submit recommendation revision log | All | Engagement Lead | A7 Revision log | Team drive | PDF
W4-04 | Week 4 | 07 Aug 2026 | Friday | 17:00 | Submit executive summary (draft) | A | Engagement Lead | Executive summary | Buddy + drive | PDF | Check-in 4
W5-01 | Week 5 | 11 Aug 2026 | Tuesday | 17:00 | Submit final report (draft for handoff) | All | Engagement Lead | Final report | Buddy + drive | PDF
W5-02 | Week 5 | 12 Aug 2026 | Wednesday | 12:00 | Submit signed Cross-Workflow Handoff Checklist | All | PM Lead | Handoff checklist | Buddy | PDF
W5-03 | Week 5 | 13 Aug 2026 | Thursday | 09:00 | BOARD PRESENTATION | All | All | Board deck | Present live | PPTX | Check-in 5
W5-04 | Week 5 | 14 Aug 2026 | Friday | 17:00 | Submit all final deliverables | All | PM Lead | All finals | Programme portal | PDF+PPTX+Excel
W6-01 | Week 6 | 17 Aug 2026 | Monday | 17:00 | Submit peer evaluation (individual, confidential) | Individual | Each member | Peer evaluation | Portal | PDF
W6-02 | Week 6 | 18 Aug 2026 | Tuesday | 17:00 | Submit reflection journal (individual) | Individual | Each member | Reflection | Portal | PDF

## Time Tracker
Weekly Time Tracker
Log hours daily. Submit to your Buddy every Friday by 17:00 ICT.
Date | Team member | Activity | Workflow (A / B / All) | Hours | Deliverable

## RACI Matrix
RACI Matrix (R = Responsible, A = Accountable, C = Consulted, I = Informed)
Task / deliverable | Eng. Lead | WF-A Lead | WF-B Lead | Member 4 | Member 5 | Member 6
Project Charter | A | R | R | R | R | R
Information credibility matrix | A | R | C | R | R | C
Analysis Requests (A) | C | A/R | C | R | I | I
Findings Memos (B) | C | C | A/R | R | R | I
Data quality report (B1) | C | C | A/R | R | R | I
Dashboard (B2) | I | C | A/R | R | R | I
Interview synthesis (A2) | C | A/R | I | R | R | I
Strategic options (A4) | A | R | C | R | R | C
Trade-off reflection (A5) | C | A/R | C | R | I | I
Validation protocol (A6) | A | R | R | R | R | R
Funding scenarios (B5) | C | I | A/R | R | R | I
Final report | A | R | R | R | R | R
Board deck | A | R | R | R | R | R
Cross-workflow handoff | A | R | R | R | R | R

## Assumption Log
Assumption Log
ID | Date | Assumption | Source | Risk if wrong | Owner | Validated? | Outcome

## Risk Register
Risk Register
ID | Risk | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status

## Decision Log
Decision Log
ID | Date | Decision | Options considered | Rationale | Dissent | Owner

## Version Control
Version Control
File | Version | Date | Author | Change | Reviewed by

## Funding Scenarios
Funding Scenarios (Task B5 / DB-5)
Use audited unit costs from D-12 and VPBank terms from D-03. State every assumption. Workflow B owns this tab.
Reference inputs
Skills Forward cost per completer (VND) | 12800000
Pathway Digital cost per completer (VND) | 6200000
VPBank grant per year (VND) | 2666666667
Current annual completers (approx.) | 2104
Broad placement rate (D-01 definition) | 71%
Formal placement rate (ST-02) | 63%
Scenario | Growth in completers | Est. total cost (VND) | Funding gap | Can meet 65% honestly? | Key risk
Hold steady | 0%
Moderate growth | +30%
Aggressive growth | +80%

## Request Log
Analysis Request Log - minimum three completed R/FM pairs before final options
Workflow A files requests. Workflow B returns Findings Memos. Engagement Lead reviews weekly. Do not share the raw dataset with A.
Request ID | Date filed | Filed by (A) | Decision question (short) | Urgency | Status | Findings Memo ID | Date returned | Returned by (B) | Notes
R-01 |  |  |  |  | Open | FM-01
R-02 |  |  |  |  | Open | FM-02
R-03 |  |  |  |  | Open | FM-03
R-04 |  |  |  |  | Open | FM-04
R-05 |  |  |  |  | Open | FM-05
R-06 |  |  |  |  | Open | FM-06
R-07 |  |  |  |  | Open | FM-07
R-08 |  |  |  |  | Open | FM-08

## Submission Checklist
Final Submission Checklist - due Friday 14 August 2026, 17:00 ICT
Deliverable | Workflow | Format | Week | Submitted? | File name
Project Charter | All | PDF | 1
RACI matrix | All | Excel | 1
Information credibility matrix | All | PDF | 1
Issue tree (A1) | A | PDF | 1
Stakeholder map (A1b) | A | PDF | 1
Analysis Requests (min. 3) | A | PDF | 2-4
Data quality report (B1) | B | PDF | 2
Findings Memos (min. 3) | B | PDF | 2-4
Interview synthesis (A2) | A | PDF | 2
Empathy and journey maps (A3) | A | PDF | 2
Dashboard (B2) | B | Excel | 2-3
Analysis summary (B3) | B | PDF | 3
Strategic options (A4) | A | PDF | 3
Evidence-check memo (B4) | B | PDF | 3
Trade-off reflection (A5) | A | PDF | 4
Validation protocol (A6) | All | PDF | 4
Funding scenarios (B5) | B | Excel | 4
Revision log (A7) | All | PDF | 4
Executive summary | All | PDF | 4-5
Final report | All | PDF | 5
Board deck | All | PPTX + PDF | 5
Handoff checklist (signed) | All | PDF | 5
Peer evaluation | Individual | PDF | 6
Reflection journal | Individual | PDF | 6