Momentum Programme   |   Scaling with Integrity

Expected Deliverables and Outcomes

Clear standards for each submission

| Client | Generation Bridge Foundation |
| --- | --- |
| Document reference | GBF Case Key |
| Classification | ANSWER KEY - FACILITATOR ONLY |
| Version | 3.1 ¦ July-September 2026 |

Use this document when marking or giving feedback. 'Excellent' is the bar for top marks; 'Minimum' is pass-level; teams below minimum on core deliverables should receive targeted buddy support.

# Summary table

| Deliverable | WS | Due | Format | Minimum acceptable | Excellent |
| --- | --- | --- | --- | --- | --- |
| Project Charter | All | Wed 29 Jul | PDF + Excel RACI | Charter confirmed; RACI has one accountable owner; A/B data rule stated. | Missing confirmations; vague scope; no named WF-A/WF-B leads. |
| A1 - Problem statement and issue tree | A | Wed 5 Aug | PDF | Hypotheses map to Analysis Requests; no overlap between branches. | Restates handbook verbatim; generic tree; no implied asks. |
| A1b - Stakeholder map | A | Thu 6 Aug | PDF | Stars match interview priority (VPBank, field staff, beneficiaries, board faction, employers). | Generic list; no sources; treats D-08 as verified fact. |
| Credibility matrix | All | Thu 6 Aug | PDF | Ratings differ by source type; justifications cite audience/incentive/definitions; contradictions noted. | All sources rated 'high' with no justification; copied from a facilitator hint. |
| Analysis Requests (min. 3) | A | Weeks 3-5 | PDF | Asks are specific enough for B to answer; emerge from transcripts/hypotheses. | Fewer than three; vague 'send us the data'; field names invented from nowhere. |
| B1 - Data quality report | B | Tue 11 Aug | PDF | Duplicates, coding, typo wage, DN double-entry, text funding row all addressed. | Silent cleaning; raw file shared with A; claims 100% clean data. |
| Findings Memos (min. 3) | B | Weeks 3-5 | PDF | Restates question; translates honestly; notes sample limitation. | Pivot dump; no caveats; raw workbook attached. |
| A2 - Interview synthesis | A | Wed 12 Aug | PDF | Themes: transport, employer quality, metric integrity, scale vs quality. | Quote dump by person; no contradictions; no citations. |
| A3 - Empathy and journey maps | A | Wed 12 Aug | PDF | Internship stage shows transport cost and employer exploitation; links to ST-05 and EP-02. | Generic persona; no quotes; outside-in design with no lived detail. |
| B2 - Performance dashboard | B | Fri 14 Aug | Excel | DN and Long An flagged; formal vs broad rate shown or footnoted. | Shared raw with A; DN hidden; single blended rate with no definition. |
| B3 - Analysis summary | B | Wed 19 Aug | PDF | Attendance correlates with placement but transport/motivation confound. | Claims attendance causes placement; ignores confounders. |
| A4 - Strategic options | A | Thu 20 Aug | PDF | Options differ on scale timing; change-my-mind trigger stated. | Three variants of 'scale more'; numbers without Request IDs. |
| B4 - Evidence-check memo | B | Fri 21 Aug | PDF | Flags if aggressive growth cannot hold 65% without selection pressure. | Rubber-stamps A without challenge. |
| A5 - Trade-off reflection | A | Wed 26 Aug | PDF | Team names the operational cost of the ethical choice, or the moral cost of the efficient choice. | Empty platitudes; no named cost; checklist of invented ED codes. |
| A6 - Validation protocol | All | Wed 26 Aug | PDF | Dong Nai recommendation cites ST-05, BN-02, EP-02 and FM findings. | Validation after the fact; fewer than six citations. |
| B5 - Funding scenarios | B | Thu 27 Aug | Excel | Aggressive scenario shows staffing gap and 65% at risk. | Assumes 65% holds automatically. |
| A7 - Revision log | All | Thu 27 Aug | PDF | Example: dropped Long An expansion after FM on DN placement. | Empty log or cosmetic edits only. |
| Executive summary | All | Fri 28 Aug | PDF | Board-ready; cites strongest evidence including Request IDs. | Buries recommendation; no limitations. |
| Final report | All | Fri 11 Sep | PDF | Integrates A narrative and B findings; trade-offs and risks included. | A and B contradict; unsourced numbers; raw data pasted. |
| Board presentation | All | Thu 10 Sep | PowerPoint | Opens with decision needed; ends with specific Board asks. | Data dump; no clear ask; A cites 'the dataset' without FM IDs. |
| Handoff checklist | All | Wed 2 Sep | PDF | Genuine exchange evidenced; Engagement Lead confirms in good faith. | One dump at the end; raw file shared; unchecked. |

# Detailed requirements by deliverable

## Project Charter (All, due Wed 29 Jul)

Requirement: Team names, roles, scope, request protocol agreed, online confirm by deadline.

Excellent: Charter confirmed; RACI has one accountable owner; A/B data rule stated.

Mark down if: Missing confirmations; vague scope; no named WF-A/WF-B leads.

## A1 - Problem statement and issue tree (A, due Wed 5 Aug)

Requirement: One precise problem sentence; MECE branches; 4+ hypotheses that imply asks for B.

Excellent: Hypotheses map to Analysis Requests; no overlap between branches.

Mark down if: Restates handbook verbatim; generic tree; no implied asks.

## A1b - Stakeholder map (A, due Thu 6 Aug)

Requirement: Power/interest grid; five starred stakeholders with cited sources.

Excellent: Stars match interview priority (VPBank, field staff, beneficiaries, board faction, employers).

Mark down if: Generic list; no sources; treats D-08 as verified fact.

## Credibility matrix (All, due Thu 6 Aug)

Requirement: Every shared D-01 to D-12 source rated H/M/L with justification; Findings Memos rated once received.

Excellent: Ratings differ by source type; justifications cite audience/incentive/definitions; contradictions noted.

Mark down if: All sources rated 'high' with no justification; copied from a facilitator hint.

## Analysis Requests (min. 3) (A, due Weeks 3-5)

Requirement: Each request states decision, hypothesis, useful answer shape, urgency; logged on Request Log.

Excellent: Asks are specific enough for B to answer; emerge from transcripts/hypotheses.

Mark down if: Fewer than three; vague 'send us the data'; field names invented from nowhere.

## B1 - Data quality report (B, due Tue 11 Aug)

Requirement: DC-01 to DC-13 found or consciously checked; cleaning logged; A gets only material issues via FM.

Excellent: Duplicates, coding, typo wage, DN double-entry, text funding row all addressed.

Mark down if: Silent cleaning; raw file shared with A; claims 100% clean data.

## Findings Memos (min. 3) (B, due Weeks 3-5)

Requirement: Plain-language answers to R-xx; definitions and caveats; curated charts only.

Excellent: Restates question; translates honestly; notes sample limitation.

Mark down if: Pivot dump; no caveats; raw workbook attached.

## A2 - Interview synthesis (A, due Wed 12 Aug)

Requirement: Thematic summary with transcript refs; contradictions flagged; questions for B listed.

Excellent: Themes: transport, employer quality, metric integrity, scale vs quality.

Mark down if: Quote dump by person; no contradictions; no citations.

## A3 - Empathy and journey maps (A, due Wed 12 Aug)

Requirement: One archetype grounded in BN-xx; pain points with quotes or FM cites.

Excellent: Internship stage shows transport cost and employer exploitation; links to ST-05 and EP-02.

Mark down if: Generic persona; no quotes; outside-in design with no lived detail.

## B2 - Performance dashboard (B, due Fri 14 Aug)

Requirement: Placement by hub/programme/gender; flag below 65%; insight-titled charts; B working file only.

Excellent: DN and Long An flagged; formal vs broad rate shown or footnoted.

Mark down if: Shared raw with A; DN hidden; single blended rate with no definition.

## B3 - Analysis summary (B, due Wed 19 Aug)

Requirement: Headline findings linked to Request/FM IDs; confounders named.

Excellent: Attendance correlates with placement but transport/motivation confound.

Mark down if: Claims attendance causes placement; ignores confounders.

## A4 - Strategic options (A, due Thu 20 Aug)

Requirement: 2-3 distinct options; every number cites R-/FM-; winners/losers named.

Excellent: Options differ on scale timing; change-my-mind trigger stated.

Mark down if: Three variants of 'scale more'; numbers without Request IDs.

## B4 - Evidence-check memo (B, due Fri 21 Aug)

Requirement: Each A option tested against Findings and D-12/D-03 feasibility.

Excellent: Flags if aggressive growth cannot hold 65% without selection pressure.

Mark down if: Rubber-stamps A without challenge.

## A5 - Trade-off reflection (A, due Wed 26 Aug)

Requirement: Open prompts answered; who gains/loses; cost of preferred path named.

Excellent: Team names the operational cost of the ethical choice, or the moral cost of the efficient choice.

Mark down if: Empty platitudes; no named cost; checklist of invented ED codes.

## A6 - Validation protocol (All, due Wed 26 Aug)

Requirement: 6+ citations including BN/ST/DN/EP and at least two R-/FM-.

Excellent: Dong Nai recommendation cites ST-05, BN-02, EP-02 and FM findings.

Mark down if: Validation after the fact; fewer than six citations.

## B5 - Funding scenarios (B, due Thu 27 Aug)

Requirement: Hold / +30% / +80% using D-12 and D-03.

Excellent: Aggressive scenario shows staffing gap and 65% at risk.

Mark down if: Assumes 65% holds automatically.

## A7 - Revision log (All, due Thu 27 Aug)

Requirement: At least one substantive change after a B challenge or Findings Memo.

Excellent: Example: dropped Long An expansion after FM on DN placement.

Mark down if: Empty log or cosmetic edits only.

## Executive summary (All, due Fri 28 Aug)

Requirement: One-sentence key message; recommendation; 90-day roadmap; honest limitations.

Excellent: Board-ready; cites strongest evidence including Request IDs.

Mark down if: Buries recommendation; no limitations.

## Final report (All, due Fri 11 Sep)

Requirement: 15-25 pages; request protocol described; every claim sourced.

Excellent: Integrates A narrative and B findings; trade-offs and risks included.

Mark down if: A and B contradict; unsourced numbers; raw data pasted.

## Board presentation (All, due Thu 10 Sep)

Requirement: Answer-first titles; Dong Nai and formal rate not hidden; cost of path named.

Excellent: Opens with decision needed; ends with specific Board asks.

Mark down if: Data dump; no clear ask; A cites 'the dataset' without FM IDs.

## Handoff checklist (All, due Wed 2 Sep)

Requirement: Both sections online-confirmed; Request Log shows min. three completed pairs.

Excellent: Genuine exchange evidenced; Engagement Lead confirms in good faith.

Mark down if: One dump at the end; raw file shared; unchecked.

# Board presentation - non-negotiables

States placement definition used and shows formal vs broad if both discussed.

Names Dong Nai underperformance or explains why recommendation still scales there.

Engages at least one ethical trade-off with a clear position.

Ends with specific decisions requested from the Board.